Case-1: Constructing a Tidal Power Plant in Saint Martin

You have recently been appointed as a project manager to make a feasibility study to test a tidal type electric power generation in Saint-Martin Island.  You have prepared a list of activities and estimated duration time, which shows as follows

| Activity code | Predecessor Activity (code) | Duration (week) |
| --- | --- | --- |
| A | - | 2 |
| B | - | 3 |
| C | A | 5 |
| D | A | 5 |
| E | B | 6 |
| F | B | 1 |
| G | B | 4 |
| H | C | 5 |
| I | C, D | 3 |
| J | E, F | 2 |
| K | H , I , J | 4 |
| L | J, G | 2 |
| M | K, L | 5 |

a. Draw the network diagram, Define the critical path, and minimum time require to complete the project

b. Determine the slack time for each activity, and Draw Gantt Chart

c. Due to resource constraints, Activity-E and F will run on 50% pace (i.e. E  will take 12 weeks to finish and F will take 2 weeks to finish), how will it impact on the project completion time?

[CLLUE: it means activity E requires extra 12-6=6 weeks , so, the impact on project completion time must be calculated based on delay of 6 weeks, not based on 12 weeks.]

e. In another scenario, due to resource constraint, it is estimated that three activities, Activity-C, H and M, will all be delayed. Activity-C will be delayed for 1 week. Activity-H will be delayed for 2 weeks. And Activity-M will be delayed for 3 weeks. What will the project completion time be in this scenario.

[CLUE: if all these 3 activities are critical, in that case total delayed time will be found by adding all the three delayed values, i.e. project will be delayed by 1+2+3= 6 weeks, as it is happening simultaneously so all delayed values must be added to get the impact on project completion time]

Case-2: Building Capacity

A company produces juice and sells to consumer market in Bangladesh. It produces three different types of juice: Mango, Orange and Papaya. The company runs 8 hours each day and 240 days in a year. Currently, the company has five machines that process fruits and convert them to juice. Each machine can produce any type of juice. Due to the negative compliance issue of a competitor, the marketing department forecasted potential increase of sale to a significant amount.

The standard processing time and forecast for each pack of each type are given below.

| Types | Mango | Orange | Papaya |
| --- | --- | --- | --- |
| Standard processing time | 3 min | 4 min | 3 min |
| Forecasting for year 2024 (packs) | 1,40,000 | 1,20,000 | 80,000 |

- Based on the information determine how many extra machines company need to acquire for next year to fulfill the forecasted market demand

[CLUE: if m/c capacity is given in hr but total processing time is found in mins in that case it must be converted into hr also and, I mean units mist be same.]

- Right now, the company is purchasing the paper package for the juice from a supplier. One of the executives suggested a business proposal for producing the packages in-house. It will cost purchasing new equipment having annual bank interest of 5,000 BDT per month and hiring staff having a fixed salary of 20,000 BDT per month. The material, energy and other operating costs would be 2 Tk per pack for the juice. Currently, the company pays 5 BDT for each pack of juices. Based on the available information, should the company decide to buy from supplier for the next year or proceed with the executives business proposal (i.e. procuring in-house of the packages)

Case-3: Calculation of EOQ

An ice cream supplier in average sells 40 liters of ice cream per month. Ordering cost is $140, and annual carrying cost is $5 per liter ice cream per year.  The supplier operates 36 weeks per year (3 weeks per month). The lead time is 4 weeks

I. Calculate the EOQ and ROP.

[CLUE: EOQ will be calculated on yearly basis, but ROP will be calculated on weekly basis as lead time and store operating information is given for week, means to calculate ROP, demand in a week will be found.]

ii. How many times per year does the store reorder?

iii.. What will be the total cost if 350 units are ordered at a time?

iv. What is the total cost if the EOQ quantity is ordered?

Case-4: Calculation of BEQ to plan Capacity

The owner of old -Fashioned Berry Pies, S. Simon, is contemplating adding a new line of pies, which will require leasing new equipment for a monthly payment of $5500. variable cost per pie would be $3 and pies would retail for $8 each.

i.  Write down the cost, revenue and profit function.

ii. How many pies must be sold in order to break even?

iii. What would be the profit if 900 pies are made and sold in a month?

iv. How many pies must be sold to realize a profit of $3500?

v. If 2000 pies can be sold and profit target is $5500, what price should be charged per pie?

Case-5: Calculation of BEQ to plan Capacity

ii. A producer of felt-tip pens has received a forecast of demand of 30,000 pens for the coming month from its marketing department. Fixed costs of $25,000 per month are allocated to the felt-tip operation, and variable costs are 37 cents (please consider, 37 cents as $0.37 dollar) per pen.

a. Find the break-even quantity if pens sell for $1 each.

b. At what price must pens be sold to obtain a monthly profit of $15,000, assuming that estimated demand materializes?